ACT HANDOVER BRIEF

Controlled top-10% review pilot and final project handover

Recommended action: Run a limited weekly pilot that reviews the highest-risk 10% of eligible orders. Keep human decision control and assess live performance, workload, and operational usefulness before changing capacity or adding modelling complexity.

1. Act scope and responsibility boundary

Purpose and process logic: Convert the validated Share-stage recommendation into a limited action plan, define how it would be evaluated, and complete the project handover.

- Analyst responsibility: Define the evidence-based action, implementation measures, evaluation rules, limitations, and handover materials.

- Business responsibility: Approve and resource the pilot, assign operational owners, conduct human reviews, and decide whether any intervention is appropriate.

- Portfolio boundary: The project proposes the action and evaluation framework but does not claim live implementation or improved delivery performance.

Process flow: validated findings -> controlled pilot -> monitored implementation -> review decision -> final handover.

2. Controlled pilot

2.1 Pilot action and evidence

Purpose: Define one proportionate starting action from the AQ1-AQ4 evidence.

- Action: Review the top 10% of eligible orders ranked by predicted late-delivery risk.

- Selection rule: Rank eligible orders from highest to lowest risk score and stop when the approved 10% capacity is reached.

- Evidence basis: The held-out-period simulation reviewed 1,353 of 13,525 orders, captured 17.37% of late orders, achieved 100.00% review precision, and produced 1.74x lift.

- Interpretation: The 10% level is a practical pilot starting point, not a proven optimal or permanent capacity.

2.2 Operating workflow and owners

Purpose: Translate the recommendation into a repeatable weekly review cycle.

| Step | Owner | Activity | Output |
| --- | --- | --- | --- |
| 1. Prepare | Analyst / reporting owner | Prepare current eligible-order data and apply the validated scoring process. | Scored eligible orders |
| 2. Queue | Reporting owner | Rank orders and select the highest-risk 10%. | Weekly review queue |
| 3. Review | Delivery / operations team | Assess queued orders and record whether follow-up is required. | Review record and action |
| 4. Complete | Data owner | Add delivery outcomes after they become available. | Completed outcome data |
| 5. Evaluate | Analyst + business owner | Compare live ranking, workload, and operational usefulness. | Pilot review decision |

Initial cadence: weekly during the controlled pilot, subject to business approval and data availability.

2.3 Human decision control

Purpose: Keep the risk ranking within its decision-support role.

- Priority only: Risk scores determine review order; they do not determine that an order will be late.

- Human assessment: Operational staff review each queued order before selecting any intervention.

- No causal claim: The analysis does not show that reviewing or intervening in a queued order will prevent late delivery.

- Pilot control: Keep the process limited until live performance, workload, and usefulness are assessed together.

3. Monitoring and evaluation

3.1 Implementation measures

Purpose: Confirm that the pilot is operated consistently and remains within the approved capacity.

- Volume: Eligible orders, queued orders, completed reviews, and percentage of eligible orders reviewed.

- Process: Review completion rate, review timing, and operational action recorded after review.

- Capacity: Compliance with the highest-risk-first rule and the approved capacity limit.

- Data quality: Missing fields, scoring failures, and changes to the eligible-order definition.

3.2 Ranking and operational outcomes

Purpose: Evaluate model-ranking performance separately from the effect of the operational review process.

- Ranking: Observed review precision, late-order recall, and lift after delivery outcomes become available.

- Delivery context: Overall late-delivery rate and late-delivery rate among reviewed orders.

- Operational value: Whether reviews were timely, produced useful follow-up, and were manageable within team capacity.

- Evaluation boundary: Strong ranking performance does not by itself prove that the review process improved delivery outcomes.

3.3 Pilot review checkpoint

Purpose: Use evidence from multiple complete review cycles to support the next business decision.

- Retain: Continue the 10% capacity if ranking performance, workload, and operational usefulness remain acceptable.

- Adjust: Change capacity only after considering workload, late-order capture, precision, and operational value together.

- Pause: Stop and investigate if data quality changes, scoring fails, or live results differ materially from the historical simulation.

4. Limitations and proportionate next steps

4.1 Limitations carried into action

Purpose: Keep the pilot recommendation within the limits of the available evidence.

- Transferability: Historical results and the retrospective simulation may not represent current, future, or live operating conditions.

- Feature scope: The ranking uses selected order-creation attributes and excludes some operational factors.

- Association scope: Shipping Mode and other analyzed attributes show associations but do not establish causation.

- Model scope: Logistic regression was evaluated on one temporal holdout and is not confirmed as the best or permanently stable model.

4.2 Next steps

Purpose: Add complexity only after live evidence identifies a clear business need.

- First priority: Prospectively validate the existing ranking and review process.

- Data update: Recheck field definitions, missingness, and category changes when new data are introduced.

- Performance update: Re-evaluate ranking metrics over time and investigate material decline.

- Future extension: Consider new features, alternative models, or formal impact evaluation only if justified by pilot results.

5. Final handover and project closure

5.1 Handover package

Purpose: Provide the materials required to understand, reproduce, communicate, and use the project outputs.

- Analysis workflow: Final Ask, Prepare, Process, Analyze, Share, and Act notebooks.

- Data outputs: Processed analysis inputs and validated result tables required by the notebooks and dashboard.

- Decision outputs: Power BI dashboard, presentation slides, presentation transcript, and this Act-stage brief.

- Technical support: Saved figures, model-evaluation outputs, capacity-scenario results, and required documentation.

5.2 Closure statement

The portfolio analysis is complete and ready for presentation and handover. It defines the problem, prepares and analyzes the data, validates a simple risk ranking, compares review-capacity scenarios, communicates the findings, and proposes a controlled pilot.

No implementation claim: This portfolio proposes a controlled pilot; it does not claim live deployment, operational intervention, or measured business improvement.